## Training Schedule
Training Schedule Sample Template
[41 empty] | Training Session name | Start Date | End Date | Duration (hours/days)
| Training Module Description | Category | Location | On-the-Job Training Form Required (OJT) | Process System or Equipment Detail | Training Provider | Instructor Name(s) | Individual Session Hours | Completion Date | Day 1 | Day 1 Start/End Time | # of Trainees | Day 2 | Day 2 Start/End Time | # of Trainees | Day 3 | Day 3 Start/End Time | # of Trainees | Day 4 | Day 4 Start/End Time | # of Trainees | Day 5 | Day 5 Start/End Time | # of Trainees | Day 6 | Day 6 Start/End Time | # of Trainees | Day 7 | Day 7 Start/End Time | # of Trainees | Operations | Maintenance | E & I | Shift A | Shift B | Shift C | Shift D | Maintenance | E & I | Other
| Maple Pumping Station Facility Operation | 1 | OMM Bayview |  | Facility | Consultant |  | 8 |  | 2016-01-01 | 08:00 - 15:00 | 6 | 2016-01-07 | 8:00 | 6 | 2016-01-14 | 8:00 | 6 | 2016-01-21 | 8:00 | 6 | 2016-01-28 | 8:00 | 6 | 2016-02-07 | 8:00 | 6 | 2016-02-14 | 8:00 | 6 | √ | √ | √ | 2015-01-01 | 2015-01-07 | 2015-01-08 | 2015-01-09 | 2015-01-11 | 2015-01-12 |  | Training Session #1 | 2015-01-01 | 2015-01-21 | 20
| Filter Backwash Process | 1 | Keswick WTP |  | Filtration | Consultant |  | 8 |  | 2016-01-01 | 12:00 - 15:00 |  | 2016-01-07 |  |  | 2016-01-14 |  |  | 2016-01-21 |  |  | 2016-01-28 |  |  | 2016-02-07 |  |  | 2016-02-14 |  |  | √ | √ | √ | 2015-01-01 | 2015-01-07 | 2015-01-08 | 2015-01-09 | 2015-01-11 | 2015-01-12 |  | Training Session #2 | 2015-01-22 | 2015-01-23 | 1
| Building area drainage sumps operation | 2 |  | yes | Area Drainage System | Contractor |  | 4 | [22 empty] | √ | √ | √ | [7 empty] | Training Session #3 | 2015-01-22 | 2015-01-28 | 6
| Fresh Air Intake Fans | 3 |  |  | HVAC | Contractor (Buffalo) |  | 2 | [23 empty] | √ | [8 empty] | Training Session #4 | 2015-01-27 | 2015-01-29 | 2
| HACH CL-17 Chlorine Analyzers | 4 |  |  | Chlorine analyzer | Contractor (HACH) | [24 empty] | √ |  | √ | [7 empty] | Training Session #5 | 2015-01-28 | 2015-02-04 | 7
[41 empty] | Training Session #6 | 2015-02-05 | 2015-02-09 | 4
[41 empty] | Training Session #7 | 2015-01-28 | 2015-02-05 | 8
[41 empty] | Training Session #8 | 2015-02-04 | 2015-02-06 | 2
[41 empty] | Training Session #9 | 2015-02-07 | 2015-02-10 | 3
[41 empty] | Training Session #10 | 2015-02-09 | 2015-02-12 | 3
[41 empty] | Training Session #11 | 2015-02-11 | 2015-02-14 | 3
[41 empty] | Training Session #12 | 2015-02-15 | 2015-02-17 | 2
Notes:
1 | Contractor responsible for coordinating instructor(s) training/demonstration with trainee availability and attendance
2 | Contractor shall provide sufficient time in the overall construction schedule to complete all required training and demonstration activities
3 | Training and demonstration sessions will generally be conducted between 8 AM and 3 PM Monday to Friday.
4 | A portion of the training sessions will be conducted on non-business hours in order to provide coverage to shift operations staff.