## Cover Page
CONTRACT NO. |  | …[Insert Region Number] |  |  |  |  | Section 01810A
|  |  |  | EQUIPMENT TESTING AND FACILITY COMMISSIONING FORMS |  |  | 2018-09-24
DATE: | [Insert Date]
Version | Date |  | Description of Revisions
1 | December 8, 2014 |  | Separate section created for all Equipment Testing and Facility Commissioning forms
2 | December 23, 2014 |  | Forms Numbered and Formatted- AAM
3 | January 14, 2015 |  | Addressed Legal Comments (JM)
4 | March 30, 2015 |  | Added edits and comments after legal review
5 | April 14, 2015 |  | Modified to align with Consultant Requirements Manual
6 | September 1, 2015 |  | Separated checklist and sign-off form. Added items to the sign-off form as request by stakeholders
7 | October 2, 2015 |  | Added Data validation SCADA tag language to Section 1.5 of Pre-Commissioning Documentation Checklist
8 | October 22, 2015 |  | Re-formatted Lock out Tag out Form. Corrected spelling errors in the Commissioning Signoff Form.
9 | November 4, 2015 |  | Updated edocs number for the water wastewater utility account and transfer form. Added asterisk.
10 | December 2, 2016 |  | Re-created in Excel format with individual sheets for each form. Pre-Commissioning checklist was also updated.
11 | January 4, 2017 |  | Updated the Pre-Commissioning Documentation Checklist clarifying three of the items.
12 | April 26, 2017 |  | Updated the Pre-Commissioning Documentation Checklist removing an unneeded item.
13 | June 14, 2017 |  | Updated the PCS Instrumentation Check listremoving 2 unneeded items. Renamed form 01810A-34 from "Panel Checklist" to "Pre-SAT Panel Checklist"
14 | August 24, 2018 |  | Added new form 01810A-35 Calibration Quality Control Checklist
15 | September 24, 2018 |  | Minor updates to 01810A-35 Calibration Quality Control Checklist Minor updates to 01810A-21 PCS Instrumentation Checklist Minor updates to 01810A-00 Pre-Commissioning Documentation Checklist
NOTE: This is a CONTROLLED Document. Any documents appearing in paper form are not controlled and should be checked against the on-line file version prior to use. Notice: This Document hardcopy must be used for reference purpose only. The on-line copy is the current version of the document.
Section 01810A |  |  |  |  | CONTRACT NO. |  | …[Insert Region Number]
2018-09-24 |  |  |  | EQUIPMENT TESTING AND FACILITY COMMISSIONING FORMS
[6 empty] | DATE: | [Insert Date]
The following forms relate to Section 01810 - Equipment Testing and Facility Commissioning
Form Code | Form Name | [5 empty] | Version
01810A-00 | Pre-Commissioning Documentation Checklist | [5 empty] | 3.2
01810A-01 | Commissioning Sign-off Form | [5 empty] | 1
01810A-02 | Request for Shutdown | [5 empty] | 1
01810A-03 | Shutdown Permit to Work | [5 empty] | 1
01810A-04 | Manufacturer's Certificate of Proper Installation | [5 empty] | 1
01810A-05 | Manufacturer's Certificate of Successful Operation | [5 empty] | 1
01810A-06 | Start Up and Performance Testing Form | [5 empty] | 1
01810A-07 | Pressure-Hydrostatic Test Reporting Form | [5 empty] | 1
01810A-08 | Consultant System Training Certification Form | [5 empty] | 1
01810A-09 | Equipment Supplier's Training Certification Form | [5 empty] | 1
01810A-10 | Inventory of Spare Parts and Tools | [5 empty] | 1
01810A-11 | Alignment Data Record Form (Retired) | [5 empty] | 1
01810A-12 | Mechanical Equipment - Installation & Startup Checklist | [5 empty] | 1
01810A-13 | Tank/Vessels Installation Checklist | [5 empty] | 1
01810A-14 | Test Report for Chemical Storage Tanks | [5 empty] | 1
01810A-15 | Pipe Installation Checklist | [5 empty] | 1
01810A-16 | Valves - Installation Checklist | [5 empty] | 1
01810A-17 | Valves - Test Report | [5 empty] | 1
01810A-18 | Electrical Equipment - Installation Checklist | [5 empty] | 1
01810A-19 | Variable Frequency/Speed Drives - Installation and Startup Checklist | [5 empty] | 1
01810A-20 | HVAC Checkout / Verification Form | [5 empty] | 1
01810A-21 | PCS Instrumentation Checklist | [5 empty] | 2.1
01810A-22 | PCS Instrumentation Calibration Checklist(Retired) | [5 empty] | 1
01810A-23 | Pre-SAT Analog I/O Loop Check | [5 empty] | 1
01810A-24 | Pre-SAT Digital I/O Loop Check | [5 empty] | 1
01810A-25 | PCS I/O Loop – Post Review | [5 empty] | 1
01810A-26 | Fibre Optic Cable Test Sheet | [5 empty] | 1
01810A-27 | Single -Mode Fibre Optic Backbone Test Sheet (Retired) | [5 empty] | 1
01810A-28 | CAT6 Horizontal Cable Pass Criteria(Retired) | [5 empty] | 1
01810A-29 | Horizontal Cable Test Signoff | [5 empty] | 1
01810A-30 | Horizontal Cable Test (Retired) | [5 empty] | 1
01810A-31 | Link Acceptance Test- Cisco Internetworking Equipment(Retired) | [5 empty] | 1
01810A-32 | Request for IPS Addresses Form | [5 empty] | 1
01810A-33 | Lock Out Tag Out Template | [5 empty] | 1
01810A-34 | Pre-SAT Panel Checklist | [5 empty] | 2
01810A-35 | Calibration Quality Control Checklist | [5 empty] | 2

## 01810A-00
Facility:
Project Name/#:
Consultant:
Contractor:
01810A-00 Pre-Commissioning Documentation Checklist
RESPONSIBILITY
It is the responsibility of the Consultant and Project Manager to facilitate the completion of this form prior to commissioning. Refer to Specification 01810 Equipment Start-up and Facility Commissioning for detailed requirements.
Project Information
Contract Number: | [5 empty] | Proposed Commissioning Date:
PROJECT COMMISSIONING TEAM
|  |  |  | Name |  |  |  | Email
REGION INTERNAL
Project Manager (CPD)
Technologist (CPD)
Construction Administrator (CPD)
Construction Coordinator (CPD)
Operations Supervisor (OMM)
Team Lead (OMM)
Capital Support Coordinator (OMM)
PCS/SCADA Representative (OMM)
Electrical Representative (OMM)
Mechnical Representative (OMM)
Regulatory Compliance Representative (S&I)
CONSULTANT
Project Manager
PCS/SCADA Integrator
Site Inspector
Commissioning Representative
CONTRACTOR
Site Supervisor
Electrical Representative
Mechanical Representative
Civil Representative
SUBCONTRACTOR
Representative
PHASE 1: PRE-COMMISSIONING DOCUMENTATION CHECKLIST
Prior to initiation of any start-up or commissioning activity, the Consultant shall prepare, consolidate, review and submit the following documentation to the Region (as applicable per project).
1.1. Factory Acceptance Testing
[6 empty] | Document Completed and Submitted |  |  | Date to be Provided By (YYYY/MM/DD)
1 | FAT records for panels (indicating all deficiencies resolved)
2 | FAT records for process equipment (indicating all deficiencies resolved)
3 | Pre-SAT software
Accepted By (Initial): |  | Consultant: |  |  |  | PM: |  |  | OMM:
Comments:
1.2 Calibration
[6 empty] | Document Completed and Submitted |  |  | Date to be Provided By (YYYY/MM/DD)
1 | *Completed 01810A-35 Calibration Quality Control Checklist - PCS/SCADA Recommendation to Proceed to SAT "Yes" Checkbox checked and signed
Accepted By (Initial): |  | Consultant: |  |  | PM: |  | OMM: |  | Auditor:
Comments:
1.3 Testing and Commissioning Plan
The Consultant shall review the Contractor's Testing and Commissioning Plan and verify that the plan meets the requirements as outlined in the Contract specifications. Testing and Commisisoning plans shall include, but not be limited to the items outlined in the Consultant Requirements Manual, Section 9.1.1, and listed below.
[6 empty] | Document Completed and Submitted |  |  | Date to be Provided By (YYYY/MM/DD)
1 | Commissioning schedule
2 | List of systems to be commissioned
3 | 24-hour emergency response plan and contacts
4 | Installation and start-up verification procedures
5 | Description of temporary systems and installations to allow for 5-day water test
6 | *5-Day water test procedures
7 | 14-Day Performance testing procedure
8 | 45-Day Operational testing procedure
9 | Watermain disinfection procedure
10 | Facility chlorination procedure
11 | Well chlorination procedure
12 | Reservoir filling plan
13 | Transition plan (operating facilities)
14 | Contingency plan (operating facilities)
15 | Completed Shutdown request form(s)
16 | Completed Shutdown permit to work form(s)
17 | Sample checklists, forms, documents for recording testing and commissioning results
Accepted By (Initial): |  | Consultant: |  |  | PM: |  | OMM: |  | Auditor:
Comments:
1.4 Draft Facility Operations Manual
It is the Consultant’s responsibility to review and comply with Section 17 – Operation Manual Guideline
of the Region’s Design Guidelines, including all associated deliverables.
Accepted By (Initial): |  | Consultant: |  |  |  | PM: |  |  | OMM:
Comments:
1.5 Equipment Manuals
It is the Consultant’s responsibility to review and comply with Section 4 – Equipment Maintenance
of the Region’s Design Guidelines, including all associated deliverables.
Accepted By (Initial): |  | Consultant: |  |  |  | PM: |  |  | OMM:
Comments:
1.6 Drawings and Diagrams
[6 empty] | Document Completed and Submitted |  |  | Date to be Provided By (YYYY/MM/DD)
1 | *As-built / red-line drawings
2 | Final power and control field wiring diagrams (i.e. Single line diagrams)
3 | *Process flow diagrams and system maps
Accepted By (Initial): |  | Consultant: |  |  | PM: |  | OMM: |  | Auditor:
Comments:
1.7 Permits and Approvals
It is the Consultant’s responsibility to arrange for and conduct inspection required by regulatory agencies and local municipalities. Depending on the project, inspection of the constructed facility or facilities may be required by some or all of the following regulatory agencies prior to operation and/or occupancy as known to the Region.
[6 empty] | Document Completed and Submitted |  |  | Date to be Provided By (YYYY/MM/DD)
Regulatory Related Permits and Approvals
1 | *MOECC Facility license (certificate of classification)
2 | *MOECC drinking water works permit
3 | *MOECC Municipal Drinking Water License
4 | *MOECC Permit to Take Water
5 | *MOECC Environmental Compliance Approval (ECA)
6 | *Registration of the activity in the MOECC Environmental Activity Sector Registry (EASR)
7 | *Documented notification to MOECC prior to or after startup
8 | *Complete NSF 60/61/372 documentation
9 | Sampling and Reporting Requirements set (Please contact Water Quality Compliance Technologist and Program Manager Water Resources Monitoring)
10 | *Written confirmation that BPOS has added regulatory compliance SCADA tags to eRIS Validation Application and ENVBI (please contact S&I Compliance Technologist)
11 | Conservation Authority authorization/permit
12 | Approvals from the Ministry of Natural Resources and Forestry
13 | Approvals from Ministry of Tourism, Culture and Sport
14 | Approvals from the Department of Fisheries and Oceans
15 | Approvals from Transport Canada (including Aeronautical Assessments)
Construction and Building Related Permits and Approvals
16 | Building occupancy permit
17 | Fire department approval for occupancy
18 | *Technical Standards and Safety Authority
19 | Electrical Safety Authority Certificate
Accepted By (Initial): |  | Consultant: |  |  | PM: |  | OMM: |  | Auditor:
Comments:
1.8 Training
[6 empty] | Document Completed and Submitted |  |  | Date to be Provided By (YYYY/MM/DD)
1 | Training Attendance Forms (blank)
2 | Lesson plans for each training session by the manufacturer’s representatives
3 | All training manuals, handouts, and visual aids
4 | Date, time, and subject of each training session (including identity and qualifications of individuals conducting training)
5 | *Training Attendance Forms (completed)
Accepted By (Initial): |  | Consultant: |  |  | PM: |  | OMM: |  | Auditor:
Comments:
1.9 Asset Management
It is the Consultant’s responsibility to review and comply with Section 21 – Development and Maintenance of Asset Inventory and Tagging of the Region’s Design Guidelines, including all associated deliverables.
[6 empty] | Document Completed and Submitted |  |  | Date to be Provided By (YYYY/MM/DD)
1 | Documentation of delivery of all spare parts and special tools
2 | *Confirmation that equipment, piping, electrical and instrumentation tagging is complete in the field
3 | *Well inspection and maintenance plan
4 | Removed equipment list
5 | *Preventive maintenance (PM) frequencies and job plans for all equipment are active in Maximo
6 | *Written confirmation from OMM that asset tagging is complete in Maximo
7 | *Completed Water and Wastewater Utility Tracking Form (eDocs: #5894838)
8 | *New operations logbook available on site
Accepted By (Initial): |  | Consultant: |  |  | PM: |  | OMM: |  | Auditor:
Comments:
1.10 Health and Safety
[6 empty] | Document Completed and Submitted |  |  | Date to be Provided By (YYYY/MM/DD)
1 | *Chemical list
2 | *Supplier or Workplace WHMIS labels (for all chemical and/or fuel storage tanks)
3 | *(Material) safety data sheets
4 | Confined space hazard assessment forms
5 | Lock-out tag-out documentation
6 | Completed Pre-Start Health and Safety determination checklist
7 | Pre-start Health and Safety Review Certificate (if triggered by above)
8 | Arc Flash Study Report
9 | *Spill kit available on site
Accepted By (Initial): |  | Consultant: |  |  | PM: |  | OMM: |  | Auditor:
Comments:
1.11 PCS / SCADA
It is the Contractor’s responsibility to review and comply with Division 13 – SCADA and Instrumentation of the Region’s Technical Specifications in its entirety, including all associated deliverables. It is the Consultant's responsiblity to review, and determine if the Contractor is complying with, Division 13 – SCADA and Instrumentation of the Region’s Technical Specifications in its entirety. These are pre-requisites to start the Witnessed Software SAT.
[6 empty] | Document Completed and Submitted |  |  | Date to be Provided By (YYYY/MM/DD)
1 | PCS Instrumentation Checklist
2 | PCS SCADA Loop – Analog Points
3 | PCS SCADA Loop – Digital Points
4 | PCS SCADA Loop – Post Review
5 | Network submittals (Both LAN and WAN)
6 | Confirmation that all devices have been assigned the correct IP, connected and, working
7 | Calibration Quality Control Checklist
8 | Pre-SAT Panel Checklist
Accepted By (Initial): |  | Consultant: |  |  |  | PM: |  |  | OMM:
Comments:
The * indicates items that will be reviewed/confirmed by the Compliance Audit Team during the Pre-Comm audit.

## 01810A-01
Facility:
Project Name/#:
Consultant:
Contractor:
01810A-01 Commissioning Signoff Form
Pre-Commissioning Documentation Checklist
☐ A representative from Strategy, Liaison and Policy Implementation (Compliance Technologist) and Operations, Maintenance and Monitoring has completed a review of 01810A-01 Pre-Commissioning Documentation Checklist.
Title |  | Print Name | Signature | Date
Consultant
York Region Project Manager
York Region Team Lead
Comments (reference attachments, if applicable):
Functional Testing (Signatures)
I confirm this phase meets the requirements set out in 01810 – Equipment Testing and Facility Commissioning.
Title |  | Print Name | Signature | Date
Consultant
York Region Project Manager
York Region Team Lead
Comments (reference attachments, if applicable):
5-Day Water Testing (Signatures)
I confirm this phase meets the requirements set out in 01810 – Equipment Testing and Facility Commissioning.
Title |  | Print Name | Signature | Date
Consultant
York Region Project Manager
York Region Team Lead
Comments (reference attachments, if applicable):
Training (Signatures)
I confirm this phase meets the requirements set out in 01820 – Demonstration and Training and the Contract Documents.
Title |  | Print Name | Signature | Date
Consultant
York Region Project Manager
York Region Team Lead
Comments (reference attachments, if applicable):
14-Day Performance Testing (Signatures)
I confirm this phase meets the requirements set out in 01810 – Equipment Testing and Facility Commissioning. *Note*. Through initiation of this phase, the newly constructed works are now feeding distribution in a water system or collection in a wastewater system.
Title |  | Print Name | Signature | Date
Consultant
York Region Project Manager
York Region Team Lead
Comments (reference attachments, if applicable):
45-Day Operational Testing (Signatures)
I confirm this phase meets the requirements set out in 01810 – Equipment Testing and Facility Commissioning.
Title |  | Print Name | Signature | Date
Consultant
York Region Project Manager
York Region Team Lead
Comments (reference attachments, if applicable):
Substantial Performance (Signatures)
I confirm this phase meets the requirements of the Contract Documents.
Title |  | Print Name | Signature | Date
Consultant
York Region Project Manager
York Region Team Lead
Comments (reference attachments, if applicable):
Final Facility Handover to York Region
Final Facility Handover to York Region can only occur when all subsequent phases have been completed and all requirements set out in the Contract Documents have been fulfilled.
Title |  | Print Name | Signature | Date
Director, CPD
Director, OMM
York Region Project Manager
York Region Team Lead
Comments (reference attachments, if applicable):

## 01810A-02
Facility:
Project Name/#:
Consultant:
Contractor:
Contractor:
01810A-02 Request for Shutdown
REQUEST FOR SHUTDOWN #_________
Project Name: |  |  | Project Number:
General Contractor: |  |  | Contract Number:
Requested By: |  |  | Date:
Facility:
Nature/Description of Shutdown and Work to be Completed:
Contingency Plan:
SHUTDOWN DETAILS:
Area of Plant:
Equipment to be Shut down:
Requested Date of Shutdown:
Alternate Date of Shutdown:
Expected Duration of Shutdown (Hours):
Expected Time Period of Shutdown: AM / PM TO AM / PM
Assigned Contractor Personnel |  | Company | Contact Info
Contractor: |  |  | Date:

## 01810A-03
Facility:
Project Name/#:
Consultant:
Contractor:
Contractor:
01810A-03 Shutdown Permit to Work
SHUTDOWN PERMIT TO WORK #_________
Project Name: |  |  |  | Project Number:
General Contractor: |  |  |  | Contract Number:
Date Of Shutdown: |  |  |  | Date:
Time Of Shutdown:
Expected Duration Of Shutdown:
Facility:
Nature/Description of Shutdown:
Requirements Placed on Contractor:
Assigned Contractor Personnel |  | Company |  |  | Contact Info
Assigned Region Personnel |  |  | Contact Info
Contractor: |  |  |  | Date:
Consultant: |  |  |  | Date:
Region: |  |  |  | Date:

## 01810A-04
Facility:
Project Name/#:
Consultant:
Contractor:
Contractor:
01810A-04 Manufacturer's Certificate of Proper Installation
Region: |  | Equipment serial no:
Equipment tag no: |  | Equipment/system:
Project no: |  | Specification section:
I hereby certify that the above-referenced equipment/system has been: (Check Applicable) Note: Attach any functional test documentation from the manufacturer.
Comments:
I, the undersigned Manufacturer’s Representative, hereby certify that I am (i) a duly authorized representative of the manufacturer, (ii) authorized by the manufacturer to inspect, approve, and operate its equipment and (iii) authorized to make recommendations required to ensure that the equipment furnished by the manufacturer is complete and operational, except as may be otherwise indicated herein. I further certify that all information con­tained herein is true and accurate.
Date:
Manufacturer:
By Manufacturer’s Authorized Representative (Authorized Signature):
Installed in accordance with the Manufacturer’s recommendations.
Inspected, checked, and adjusted.
Serviced with the proper initial lubricants.
Electrical and mechanical connections meet quality and safety standards.
All applicable safety equipment has been properly installed.
Functional tests.

## 01810A-05
Facility:
Project Name/#:
Consultant:
Contractor:
01810A-05 Manufacturer's Certificate of Successful Operation
Region: |  | Equipment serial no:
Equipment tag no: |  | Equipment/system:
Project no: |  | Specification section:
I hereby certify that the above-referenced equipment/system: (Check Applicable) Note: Attach any performance test documentation from the manufacturer.
Comments:
I, the undersigned Manufacturer’s Representative, hereby certify that I am (i) a duly authorized representative of the manufacturer, (ii) authorized by the manufacturer to inspect, approve, and operate its equipment and (iii) authorized to make recommendations required to ensure that the equipment furnished by the manufacturer is complete and operational, except as may be otherwise indicated herein. I further certify that all information con­tained herein is true and accurate.
Date:
Manufacturer:
By Manufacturer’s Authorized Representative (Authorized Signature):
Has been performance tested
Is in full operating condition
Is operating in accordance with the specified design rating
Is in full warranty condition
Adjoining pipe is properly and independently supported so as not to cause undue stress that would, otherwise, be detrimental to the equipment performance

## 01810A-06
Facility:
Project Name/#:
Consultant:
Contractor:
01810A-06 Startup and Performance Testing Form
Unit Process Description: (Include description and equipment number of all equipment and devices):
Startup Procedure (Describe procedure for sequential startup and evaluation, including valves to be opened/closed, order of equipment startup, etc.):
Startup Requirements (Water, power, chemicals, etc.):
Evaluation Comments:
CONTRACTOR Certification that Unit Process is capable of performing its intended function(s), including fully automatic operation:
General Contractor Name:
Contractor’s Startup Representative (Authorized Signature): |  | Date:

## 01810A-07
Facility:
Project Name/#:
Consultant:
Contractor:
01810A-07 Pressure-Hydrostatic Test Reporting Form
Date Installation Complete:
Tank # / Pipe Description:
Material & Size:
Pre-Start-Up |  |  | Checked By (Initial) | Date |  | Result / Remarks
Valves or Plugs
Test Pressure
Duration of Test
Leakage
Meter Reading Pre-Test
Meter Reading Post-Test
*Indicate (N/A) if not applicable
Inspection Result | Passed Installation and Start-Up checkout. Equipment certified |  |  |  | Failed – Contractor to schedule re-inspection.
Notes:
Authority |  | Name |  | Signature |  |  | Date
Consulting Engineer1
Contractor1
Subcontractor1
Owner1
1Signatures above do not absolve the Contractor from any portion of the contractual obligations.

## 01810A-08
Facility:
Project Name/#:
Consultant:
Contractor:
01810A-08 Consultant System Training Certification Form
Instructions Provided To (List Operating Staff)1 |  |  | Date | Comments
1This is to certify that all required York Region Operations Staff have received the appropriate system training and are ready to assume operation of the facility.
Authority | Name |  | Signature |  | Date
Consultant
York Region Project Manager
York Region Operations Supervisor

## 01810A-09
Facility:
Project Name/#:
Consultant:
Contractor:
01810A-09 Equipment Supplier's Training Certification Form
Equipment Description:
Tag #: |  |  | Date of Install:
Manufacturer/Supplier:
Model #: |  |  | Serial #:
Specification Section:
Operations Check List |  | Instructor1 |  | Date | Comments
Start-Up Procedure Reviewed
Shutdown Procedure Reviewed
Normal Operation Procedure Reviewed
Other:
Maintenance Check List |  | Instructor1 |  | Date | Comments
Described Normal Oil Changes (Frequency)
Described Special Tools Required
Described Normal Items to be Reviewed for Wear
Described Preventive Maintenance Instructions
Described Greasing Frequency
Other:
Instructions Provided To (List Operating Staff)1 |  |  |  | Date
1The Manufacturer/Supplier hereby certifies that a factory trained service technician has instructed the Region’s operating personnel in the proper operation and maintenance of the equipment designated herein. If the item is not applicable note N/A.
Authority | Name |  | Signature |  | Date
Consulting Engineer2
Contractor/Subcontractor2
Manufacturer/Supplier2
Owner
2The signatures above do not absolve the Contractor from any of the contractual obligations.

## 01810A-10
Facility:
Project Name/#:
Consultant:
Contractor:
01810A-10 Inventory of Spare Parts and Tools
Date | Division / Clause |  | Equipment | Accepted by Consultant | Accepted by Region

## 01810A-12
Facility:
Project Name/#:
Consultant:
Contractor:
01810A-12 Mechanical Equipment - Installation & Startup Checklist
Equipment: |  |  |  |  | Tag No.:
Record of : | Alignment Error Check |  |  |  | Shim correction Calculation Provided
Final Check
Method Used | Indicator Reversed |  |  |  | Rim and Face
Reading in | mm |  | inches |  | Sag
Cold Offset | Horizontal |  |  |  | Vertical
Alignment Field Data Notes:
Authority |  | Name |  | Signature |  |  | Date
Consulting Engineer2
Contractor2
Mech. Subcontractor2
Owner2
2Signatures above do not absolve the Contractor from any portion of the contractual obligations
Equipment Type: | [5 empty] | Tag #:
Manufacturer:
Model #: |  |  |  | Serial #:
Checklist |  |  | Checked By1 | Date |  | Comments
Shop Drawings Received
Code Certificates Received
Foundation Grout (Base, anchor bolts, base plate level, etc.)
Exterior Finish
Connections (Piping, fittings, chutes, etc.)
Supplied Lifting Devices in Place
Nameplate & Data
Equipment Identification
Alignment
Removal of Shipping Oil/Rust Preventative
External/Internal Coatings
Initial Lubrication
Equipment Safety Devices & Guards
Free Movement
Belt or Chain Drives, Couplings
Lubrication System/Piping Installed
All Equipment Accessories in Place (Gauges, drains, pressure relief valves, seal water, etc.)
MCCR Canadian Registration # (s)
Electrical Safety Devices Functioning
Electrical/Instrumentation Test Checklist Completed
Operation & Maintenance Manuals Received
Manufacturer’s Letter of Installation Received
Manufacturer’s Letter of Operation Received
Manufacturer’s Letter of Training Received
Spare Parts Received
1Indicate N/A in “Checked By” field if item is not applicable.
Startup |  |  | Checked By1 | Date |  | Comments
Manufacturer’s Representative in Attendance
Performance As Per Specification
Vibration
Temperature of Parts
Alignment Re-Check After Run
Noise
Notes:
1Indicate N/A in “Checked By” field if item is not applicable.
Authority |  | Name |  | Signature |  |  | Date
Consulting Engineer2
Contractor/Subcontractor2
Owner2
2Signatures above do not absolve the Contractor from any portion of the contractual obligations

## 01810A-13
Facility:
Project Name/#:
Consultant:
Contractor:
01810A-13 Tank/Vessels Installation Checklist 01810A-13 Tank/Vessels Installation Checklist
Tank/Vessel Location:
Tank/Vessel Contents:
Parameters |  | A | B | C | D | Date | Inspected By1 | Comments
1. Quantity of Tanks
2. Volume
3. Drain Isolation Valve
4. Manway with Removable Lid
5. Level Indicator
6. Flanged Connections for Level Monitoring
7. Lifting Lugs
8. Venting
9. Secondary Containment
1Indicate N/A in “Inspected By” field if item is not applicable.
Legend:
(A) Inspected and found acceptable
(B) Inspected, found defective but corrected
(C) Inspected, found defective and not corrected
(D) Not inspected
Inspection Results |  | PASSED installation and start-up checkout. Equipment is Certified and ready for service. |  |  |  |  | FAILED – Contractor to schedule equipment re-inspection.
|  |  |  | Yes |  | No | Comments
Manufacturer’s Letter of Operation Received
Notes:
Authority |  |  | Name |  |  | Signature |  | Date
Consulting Engineer2
Contractor/Subcontractor2
Owner2
2Signatures above do not absolve the Contractor from any portion of the contractual obligations

## 01810A-14
Facility:
Project Name/#:
Consultant:
Contractor:
01810A-14 Test Report for Chemical Storage Tanks 01810A-13 Tank/Vessels Installation Checklist
Tank Contents:
Supplier:
Volume (L): | [5 empty] | Quantity of Tanks:
Dimensions (D in m) x (H in m): | [5 empty] | Conditions of Service:
Tank Material:
General Chemical Storage Tank
|  | Yes | No | N/A | Date | Inspected By | Comments
1. Flanged connections as per contract drawings
2. Cover is bolted on to obtain gas tight seal
3. Drain isolation valve at discharge points as per drawings
4. Valves compatible with conditions of service
5. PVC pipe level indicator on exterior of tank
6. Sight glass is protected
7. Day tank to be set on non-corrosive support stand 600 mm off floor
8. Nozzles flush with inside surface of tank
9. Rated for flanged nozzles
General Chemical Storage Tank
|  | Yes | No | N/A | Date | Inspected By | Comments
10. Pipe supports in place
11. Tank insulation and heat tracing
Notes:
Concrete Storage Tank
|  | Yes | No | N/A | Date | Inspected By | Comments
1. Flanged connections as per contract drawings
2. Cover is bolted on to obtain gas tight seal
3. Drain isolation valve at discharge points as per drawings
4. Valves compatible with conditions of service
5. PVC pipe level indicator on exterior of tank
6. Sight glass is protected
Notes:
|  |  | Yes | No | Comments
Manufacturer’s Letter of Operation Received
Notes:
Authority | Name |  |  | Signature |  |  | Date
Consulting Engineer1
Contractor/Subcontractor1
Owner1
1Signatures above do not absolve the Contractor from any portion of the contractual obligations

## 01810A-15
Facility:
Project Name/#:
Consultant:
Contractor:
01810A-15 Pipe Installation Checklist 01810A-13 Tank/Vessels Installation Checklist
Reference Points Regarding Location
From:
To:
Parameters |  |  |  | Yes | No | N/A | Date | Inspected By1 | Comments
1. Pipe Material
2. Diameter
3. Pressure Class/Rating
4. Hydro Static Test Results
5. Pipe Colour
6. Pipe Encasement
7. Secondary Containment
8. Leak Detection System
9. Pipe Support
1Indicate N/A in “Inspected By” field if item is not applicable.
Legend:
(A) Inspected and found acceptable
(B) Inspected, found defective but corrected
(C) Inspected, found defective and not corrected
(D) Not inspected
Inspection Results |  | PASSED installation and start-up checkout. Equipment is Certified and ready for service. | [5 empty] | FAILED – Contractor to schedule equipment re-inspection.
|  |  |  | Yes | No | Comments
Manufacturer’s Letter of Operation Received
Notes:
Authority |  |  | Name |  |  |  | Signature |  |  | Date
Consulting Engineer2
Contractor/Subcontractor2
Owner2
2Signatures above do not absolve the Contractor from any portion of the contractual obligations

## 01810A-16
Facility:
Project Name/#:
Consultant:
Contractor:
01810A-16 Valves – Installation Checklist 01810A-16 Valves – Installation Checklist
Valve Identification: |  |  | Pipe Identification:
Serial #: |  |  | Tag #:
Location: |  |  | Max. Service Pressure:
General |  | Checked By1 | Date | Comments
Shop Drawings Received
Code Certifications Received
Supported Properly
Nameplates & Data
Equipment Identification
Body |  | Checked By1 | Date | Comments
Manufacturer & Model #
Valve Type
Size
End Connection
Trim Form
Packing/Stem Seal Adjustment
Lubrication
Exterior Finish
Actuator |  | Checked By1 | Date | Comments
Manufacturer & Model #
Type
Open At/Close At
Fail Position
Handwheel/Manual Override Position Indicator
Open/Closed Position Stop Adjustment
Lubrication
Electrical/Instrumentation Test Checklist Complete
Positioner/Limit Switch |  | Checked By1 | Date | Comments
Manufacturer & Model #
All Accessories Installed & Functioning Correctly (Filter/Regulator, Gauge, Bypass, etc.)
Input Signal/Output Signal
Calibration
Performance |  | Checked By1 | Date | Comments
Manufacturer’s Representative in Attendance
Maximum Flow
Valve % Open @ Max. Flow
Inlet Pressure @ Max. Flow
Pressure Drop @ Max. Flow
Other |  | Checked By1 | Date | Comments
Valve Tested With Piping (Do not operate during test)
Valve Operated After Pressure Tests
MCCR Canadian Registration # (s)
Manufacturer’s Letter of Operation Received
Spare Parts Received
Operation & Maintenance Manuals Received
Manufacturer’s Letter of Operation Received
Manufacturer’s Letter of Training Received
Notes:
1Indicate N/A in “Checked By” field if item is not applicable.
Authority | Name |  | Signature |  | Date
Consulting Engineer2
Contractor/Subcontractor2
Owner2
2Signatures above do not absolve the Contractor from any portion of the contractual obligations

## 01810A-17
Facility:
Project Name/#:
Consultant:
Contractor:
01810A-17 Valves – Test Report 01810A-16 Valves – Installation Checklist
Valve Identification: |  |  | Pipe Identification:
Serial #: |  |  | Tag #:
Location: |  |  | Max. Service Pressure:
Body |  | Checked By1 | Date | Comments
Manufacturer & Model #
Valve Type
Size
End Connection
Trim Form
Packing/Stem Seal Adjustment
Lubrication
Exterior Finish
Actuator |  | Checked By1 | Date | Comments
Manufacturer & Model #
Type
Open At/Close At
Fail Position
Handwheel/Manual Override Position Indicator
Open/Closed Position Stop Adjustment
Lubrication
Electrical/Instrumentation Test Checklist Complete
Positioner/Limit Switch |  | Checked By1 | Date | Comments
Manufacturer & Model #
All Accessories Installed & Functioning Correctly (Filter/Regulator, Gauge, Bypass, etc.)
Input Signal/Output Signal
Calibration
Performance |  | Checked By1 | Date | Comments
Manufacturer’s Representative in Attendance
Maximum Flow
Valve % Open @ Max. Flow
Inlet Pressure @ Max. Flow
Pressure Drop @ Max. Flow
Other |  | Checked By1 | Date | Comments
Valve Tested With Piping (Do not operate during test)
Valve Operated After Pressure Tests
MCCR Canadian Registration # (s)
Manufacturer’s Letter of Operation Received
Notes:
1Indicate N/A in “Checked By” field if item is not applicable.
Authority | Name |  | Signature |  | Date
Consulting Engineer2
Contractor/Subcontractor2
Owner2
2Signatures above do not absolve the Contractor from any portion of the contractual obligations

## 01810A-18
Facility:
Project Name/#:
Consultant:
Contractor:
01810A-18 Electrical Equipment - Installation Checklist
Equipment Tag | Description | Maximo ID | Manufacturer | Model # | Serial # | Nameplate |  |  |  | Motor Checks |  |  |  | Control Checks
[6 empty] | Size |  | Voltage (Volts) | Full Load Amps | Rotation Check | Motor Current(Amps) |  |  | Operation (yes/no) |  | E-Stops | Interlocks
[6 empty] | HP | kW |  |  | (Yes/No) | Phase A | Phase B | Phase C | Local | Remote | (Yes/No) | (Yes/No)

## 01810A-19
Facility:
Project Name/#:
Consultant:
Contractor:
01810A-19 Variable Frequency/Speed Drives – Installation & Startup Checklist
Equipment Description:
Manufacturer: |  |  | Date of Install:
Model #: |  |  | Serial #:
Pre-Start |  | Checked By1 | Date | Masured Value | Comments
Wiring
Tagging Nameplates
Fuse/Overload Ratings Checked
Drive Properly Grounded
Signal and Input/Output Power Wiring Run in Separate Conduits
Direction of Motor Rotation
Input Voltage
Speed Control Signal
Horsepower Rating
Max. Speed Setting
Min. Speed Setting
Acceleration Rate Setting
Deceleration Rate Setting
Operation & Maintenance Manuals Submitted
Spare Parts Received
Startup (in presence of Manufacturer Representative) |  | Checked By1 | Date | Masured Value | Comments
Performance per Spec. / Data Sheet
Local Start / Stop
Remote Start / Stop
Local Speed Selection
Remote Speed Selection
Drive Run / Fault Indication
Drive Run / Fault Indication
Duration of Initial Run (Minimum 1 hour)
Receipt of Letter from Manufacturer Confirming Proper Installation of Equipment
Comments:
1Indicate N/A in “Checked By” field if item is not applicable.
Speed [RPM]2 | Flow [L/s] | Motor Voltage [Volts] | Motor Current [Amps] |  | Motor Frequency [Hz]
Comments:
Inspection Results | PASSED installation and start-up checkout. Equipment is Certified and ready for service. |  |  | FAILED – Contractor to schedule equipment re-inspection.
2Measure from the minimum speed to maximum speed at 25% increments
Authority |  | Name | Signature |  |  | Date
Consulting Engineer3
Contractor/Subcontractor3
Owner3
System Integrator3
Supplier3
3Signatures above do not absolve the Contractor from any portion of the contractual obligations

## 01810A-20
Facility:
Project Name/#:
Consultant:
Contractor:
01810A-20 HVAC Checkout / Verification Form
Date Verification Performed:
HVAC System |  | Area
Total Number of Zone Control |  |  | Total Number of Electric Splitter Dampers
Total Number of Electric Control Dampers |  |  | Total Number of Makeup Air Unit
Total Number of Exhaust Fan |  |  | Total Number of Automatic Backdraft Damper
Total Number of Damper
Zone No.
Number of Air Diffusers |  |  | Number of Splitter Dampers
Air Diffuser No. 1 Designed Output (cfm) |  |  | Number of Volume Dampers
Air Diffuser No. 1 Actual Output (cfm) |  |  | Makeup Air No. 1 Rated Capacity
Air Diffuser No. 2 Designed Output (cfm) |  |  | Exhaust Fan No. 1 Rated Capacity
Air Diffuser No. 2 Actual Output (cfm) |  |  | Interlocks Verified for Proper Operation
(To be completed for the total number of air diffusers in the zone) |  |  | Proper Temperature Control Verified
Notes:
Authority | Name |  | Signature | Date
Consulting Engineer1
Contractor1
HVAC/Mech. Subcontractor1
Owner1
1Signatures above do not absolve the Contractor from any portion of the contractual obligations

## 01810A-21
Facility:
Project Name/#:
Consultant:
Contractor:
01810A-21 PCS Instrumentation Checklist
Equipment Tag | Description | Maximo ID | Transmitter |  | Sensor |  | Calibrated Range |  | Pre-Start up(Checked by Consultant) |  |  |  |  | Calibration |  |  |  |  | Pass/ Fail | Instrument Parameters
[9 empty] | Electrical Installation Conformance |  | Mechanical Installation |  | Spare Parts | Test Equipment / Standards Calibration Reports | Calibration Date | Factory Report | Label | Site Calibration Completed |  | Soft File | Printout
|  |  | Model # | Serial # | Model # | Serial # | Range | Units | Transmitter | Sensor | Transmitter | Sensor
XXYYZZ_PROC_EQUIP_SUBEQUIP

## 01810A-23
|  |  |  | Facility: | [6 empty] | System Integrator:
Project Name/#:
Consultant:
Contractor:
01810A-23 Pre-SAT Analog I/O Loop Check
PAC: | <Description> |  |  |  |  | Test Values |  |  |  |  | System Integrator |  | Contractor |  | Consultant |  | Comments
Rack | Slot | Card | Address | Tag | Description | 0% | 25% | 50% | 75% | 100% | Initial | Date | Initial | Date | Initial | Date
Examples
0 | 12 | 1756-IF8H | I:12.0 | WWEL1_LIT1_AI | Wetwell 1 Level Indication
|  |  | I:12.1 | GEN_TK1_LIT1_AI | Diesel Tank Level Indication
I:12.2
I:12.3
I:12.4
I:12.5
I:12.6
I:12.7
0 | 15 | 1756-OF6CI | O:15.0 | RSP_PMP1_SPD_AO | Pump 1 Speed Setpoint
O:15.1
O:15.2
O:15.3
O:15.4
O:15.5

## 01810A-24
|  |  | Facility: | [7 empty] | System Integrator:
Project Name/#:
Consultant:
Contractor:
01810A-24 Pre-SAT Digital I/O Loop Check
PAC: | <Description> |  |  |  |  | Configuration |  | Test Values |  |  | System Integrator |  | Contractor |  | Consultant |  | Comments
Rack | Slot | Card | Address | Tag | Description | N/C | N/O | 0 | 1 | Jumpered (Yes/No) | Initial | Date | Initial | Date | Initial | Date
Examples
0 | 5 | 1756-IB16 | I:5/0 | RSP_PMP1_ESTP_DI | Pump 1 Emergency Stop
|  |  | I:5/1 | RSP_PMP1_LIT1_BKUP_DI | Pump 1 LIT Mode
I:5/2
|  |  | I:5/3 | PCS_CP1_PL1_ALRM_DO | Control Panel General Alarm Pilot Light
I:5/4
I:5/5
I:5/6
I:5/7
I:5/8
I:5/9
I:5/10
I:5/11
I:5/12
I:5/13
I:5/14
I:5/15
0 | 10 | 1756-OB16I | O:10/0 | PCS_CP1_PL1_ALRM_DO | Control Panel General Alarm Pilot Light
O:10/1
O:10/2
O:10/3
O:10/4
O:10/5
O:10/6
O:10/7
O:10/8
O:10/9
O:10/10
O:10/11
O:10/12
O:10/13
O:10/14
O:10/15

## 01810A-25
|  | Facility: |  | System Integrator:
Project Name/#:
Consultant:
Contractor:
01810A-25 PCS I/O Loop – Post Review
Discussion Points
□ Discussion of deficiencies and concerns
□ Schedule date to complete I/O checks for any missing or deficient I/O points
□ Review proposed SAT date(s)
□ New Business
PAC: | <Description> |  | Acceptance
IO Point Address | Deficiency Description |  | Contractor |  | System Integrator |  | Consultant
|  |  | Initial | Date | Initial | Date | Initial | Date

## 01810A-26
Facility:
Project Name/#:
Consultant:
Contractor:
System Integrator:
01810A-26 Fibre Optic Cable Test Sheet
Tests passed and were submitted (check the appropriate box) |  |  | Yes | No
Consultant (signature):

## 01810A-29
Facility:
Project Name/#:
Consultant:
Contractor:
01810A-29 Horizontal Cable Test Signoff
Tests passed and were submitted (check the appropriate box) |  | Yes | No
Consultant (signature):

## 01810A-32
Facility:
Project Name/#:
Consultant:
Contractor:
01810A-32 Request for IPS Addresses Form
Contractor Information | [5 empty] | Information
Date Submited: | [5 empty] | Completed By:
Requested By: | [5 empty] | Contact Tel:
Contact Tel: | [5 empty] | Contact Email:
Contact Email: | [5 empty] | Date Required:
Date Required:
| Contractor | [8 empty] | Region
Item | Manufacturer | Make/Model | Description of Device | Bandwidth Requirements (Kbps or Mbps) | Location |  |  |  |  | Assigned IP | Assigned Subnet | Assigned Gateway
[5 empty] | Building |  | Floor | Room | Device Connected to Access Closet
1 | Allen-Bradley | 1756-EN2T | ControlLogix Ethernet/IP Communication Card | Auto negotiate 10/100/1000Mbps | Control Building |  | 1 | PAC Panel | WAO | 172.18.130.94 | 255.255.255.224 | 172.18.130.65
2
3
4
5
6
7
8
9
10
11
12

## 01810A-33
Facility:
Project Name/#:
Consultant:
Contractor:
01810A-33 Lock Out Tag Out Template
Location: | [7 empty] | Location ID:
Area: |  |  | Date of Verification: |  |  |  |  | Version:
Description of Service Work
ONLY TRAINED AND AUTHORIZED PERSONNEL SHALL CONDUCT LOCKOUT PROCEDURES
Resources Required
CEL,CML, SL & T depending on work PL per person Chain LOTODevices
CEL-common electrical lock CM+J14L-common mechanical lock PL- Personal Lock SL -Station Lock T-Tag
PPE Hard Hat Gloves Safety Shoes Goggles Face Shield For Confined Space Entry, please check CSE procedure for details
Location: | [7 empty] | Location ID:
Area: |  |  | Date of Verification: |  |  |  |  | Version:
Description of Service Work ☐Motor Repair ☐ Pump Repair ☐ Pump Inspection ☐ Clean Up ☐ Motor Exchange ☐ Pump Exchange ☐ Others ___________________
ONLY TRAINED AND AUTHORIZED PERSONNEL SHALL CONDUCT LOCKOUT PROCEDURES
1- 2- 3- 4-
De-Energizing Procedure
1. # | 2. Energy Type | 3. Energy Source(s) |  | 4. Asset ID | 5. Lockout Location | 6. LOTO Devices | 7. Procedure for de-energizing and locking out |  | 8. Verification of zero energy
IF LOCKOUT PROCEDURES CANNOT BE COMPLETED OR VERIFIED, STOP AND NOTIFY YOUR SUPERVISOR
Energizing Procedure 1- 2- 3- 4- 5-
Location: | [7 empty] | Location ID:
Area: |  |  | Date of Verification: |  |  |  |  | Version:
Description of Service Work
ONLY TRAINED AND AUTHORIZED PERSONNEL SHALL CONDUCT LOCKOUT PROCEDURES
1- 2- 3- 4-
Verified by
(Team Lead)
(MM/DD/YY)
Signed off by
Name and Signature
(Manager/Superintendent)
|  |  |  | Operations Maintenance and Monitoring |  |  |  |  | (MM/DD/YY)
Signed off by
Name and Signature
(Manager/Superintendent)
|  |  |  | Centralized Maintenance Support |  |  |  |  | (MM/DD/YY)
Other:
Pump Exchange
Motor Exchange
Clean Up
Pump Inspection
Pump Repair
Motor Repair
Other:
Pump Exchange
Motor Exchange
Clean Up
Pump Inspection
Pump Repair
Motor Repair

## 01810A-34
|  | Facility: | System Integrator:
|  | Project Name/#: | Region PCS
Consultant:
Contractor:
01810A-34 Pre-SAT Panel Checklist
PAC: | <Description> |  | Contractor |  | System Integrator |  | Consultant |  | Region PCS |  | Comments
Item | Test/Inspection Parameter |  | Initial | Date | Initial | Date | Initial | Date | Initial | Date
Pre-Installation | Review panel FAT deficiencies
Confirm panel FAT deficiencies have been addressed and corrected
Current panel drawings included
Panel set in correct location
Visual inspection to ensure free from defects (scratches/debts/holes)
Equipment in good condition and not damaged
Enclosure | Enclosure manufacturer matches shop submission
Panel free from defects (scratches/dents/holes)
No blanked holes (indication of error in cutting)
No unnecessary holes present
Panel is free from metal shavings and debris (cleaned)
Wiring & Power Supplies | Internal panel wiring is #16AWG
DC control wiring is blue, #16AWG
AC control wiring is red, #16AWG
Interlock wiring energized from external source is yellow, #16AWG
Analog wiring is shield twisted pair, #18AWG
Internal AC digital signal wiring is red (hot), white (neutral), green (ground) #16AWG
AC digital signal (control from panel) wiring is red (control), black (hot), white (neutral), green (ground) #16AWG
AC digital signal (control from external) wiring is yellow (control), black (hot), white (neutral), green (ground) #16AWG
120VAC (power) wiring is black, #16 AWG
120VAC (neutral) wiring is white, #16 AWG
24V DC Distribution wiring is dark blue (+), #16 AWG
24V DC Distribution wiring is light blue (-), #16 AWG
DC Grounding wire is green, #16 AWG
Instrument ground wiring is green with white stripe, #6 AWG
Control circuit ground wiring is dark green, #6 AWG
Field wiring, #14 AWG
Tug test on 10% of wires – confirm secure to Terminals
Wires neatly organized in raceway – no more than 50% filled, raceways white in colour
Wire tagging conforms to SCADA standards (Style & Font)
Wire tags are visible without manipulation of wire
All wires are labeled – (Check of text in following section)
Wires are bundled with Velcro style wraps not ty-wraps
Wires to panel door bundled in spiral wrap not ty-wraps
No splices or marrettes are utilized
No wiring passes over top TBs or under DIN rail

## 01810A-35
Facility:
Project Name/#:
Consultant:
Contractor:
01810A-35 Calibration Quality Control Checklist
Instrument Numbers (by tag name):
Shop Drawing Review |  | Consultant þ | CPD þ | PCS/SCADA þ | Notes
Shop Drawings - Submitted by Contractor for each instrument listed
Shop Drawing Numbers:
Shop Drawings - Verified to detail all of the necessary information for each instrument listed in accordance with Specification 13930, Section 1.3 Submittals
Form 1810A-21 - Submitted by Contractor
Form 1810A-21 - Verified completion of columns by Contractor: Equipment Tag, Description, Maximo ID, Transmitter Model and Serial #, Sensor Model and Serial #, Calibrated Range
Calibration and Start-up Procedures - Submitted by Contractor for each instrument listed
Calibration and Start-up Procedures- Verifed to be in accordance with instrument specifications
Sample Calibration Reports - Submitted by Contractor
Sample Calibration Reports - Verified to conform to Region acceptable report forms
Consultant Name/Signature/Date
CPD Representative Name/Signature/Date
PCS/SCADA Representative Name/Signature Date
Start-Up On Site (*Verify prior to Contractor leaving site) |  | Consultant þ | Notes
Qualifications of technician - Provided by Contractor
Qualifications of technician - Verified by Consultant
Calibration certificates for test equipment - Submitted by Contractor for all test equipment
Calibration certificates for test equipment - Verified to be valid (less than 1 year); calibration standards are not expired
Calibration stickers - Verified to have been placed on all calibrated instruments
Form 1810A-21 - Completed columns (by Consultant): Test Equipment Calibration Reports, Calibration Date, Factory Report, Label, Site Calibration Completed
Consultant Name/Signature/Date
Post Start-Up |  | Consultant þ | CPD þ | PCS/SCADA þ | Notes
Calibration Reports for all instruments - Submitted by Contractor
Calibration Reports for all instruments - Verfied to conform to Region acceptable report forms; must be in Excel; not handwritten or scanned
Calibration Reports for all instruments - Verified the following sections: - Instrument Information - All filled out - As Found Performance - % of MPE <100% - As Left Performance - % of MPE <100% - Test Equipment - Listed and calibrated, standard hasn't expired - Error Percent Graph - Error is within the tolerance for instrument - Conformity - Marked as conforms - Technician Identification and Signature - All filled out and signed
Instrument Parameters - Verfied that pdf printout and electronic file (where available) submitted by Contractor
Form 1810A-21 - Completed columns (by Consultant): Pass/Fail, Instrument Parameters Soft File, Printout
Consultant Name/Signature/Date
CPD Representative Name/Signature/Date
PCS/SCADA - Recommendation to Proceed to SAT |  |  | Yes |  | No
Additional Comments:
PCS/SCADA Representative Name/Signature Date

## Data (hidden)
Options
Yes
No
Not Applicable
Number of Tanks
1
2
3
Tank Material
FRP
XLPE
Concrete
PE
Other