## 60% Submission
Northeast Vaughan Water Servicing - Elevated Tank Contract
Contract Specification Tracking Log
|  | 60% - 1st Submission | [5 empty] | 100% - 2nd Submission |  |  |  |  | 3rd Submission
Spec | Description/Name | YR Review | Bid Form Item# | Latest Template Version | Comments/Status | ETO Comments | YR Response | Note from ETO | YR Review - 100% Submission | Status | Reviewed Date | Status | Reviewed Date | Status
Front End
Bid Form
Contract Info Form
Supplementary Conditions
Instructions to Bidders
DIV 1 | General Requirements
TOC
1000 | General Requirements |  | Included but not measured separately
1010 | Summary Of Work |  | Included but not measured separately
1025 | Measurement and Payment |  | Included but not measured separately
1035 | Amending and Supplementing Contract Documents |  | Included but not measured separately
1040 | Coordination |  | Included but not measured separately
1060 | Regulatory Requirements |  | Included but not measured separately
1092 | Abbreviations |  | Included but not measured separately
1200 | Project Meetings |  | A1.01
1200A | Pre-Construction Meeting Agenda Template |  | Included but not measured separately
1250 | Substitutions |  | Included but not measured separately
1300 | Submittals |  | Included but not measured separately
1310 | Construction Schedules |  | A1.02
1310A | Facility Schedule Template |  | Included but not measured separately
1351 | Health and Safety |  | Included but not measured separately |  | `
1400 | Quality Control |  | A1.03
1420 | References |  | Included but not measured separately
1425 | Computerized Maintenance Management System |  | A1.04
1430 | Operation and Maintenance Data |  | A1.05
1450 | As-Built Drawings |  | A1.06 |  | Fixed LS of $100k
1450A | Declaration of Complete and Accurate As-Builts |  | Included but not measured separately
1501 | Construction Sequencing |  | Included but not measured separately
1505 | Mobilization and Demobilization |  | A1.07
1520 | Field Office |  | A1.08
1550 | Traffic Control |  | A1.09
1561 | Environmental Protection |  | A1.10
1561A | Consultants, Contractors and Suppliers IMS Performance |  | Included but not measured separately
1600 | Material and Equipment |  | Included but not measured separately
1640 | Manufacturer's Services |  | Included but not measured separately
1710 | Pre-Construction Structural Survey |  | A1.11
1720 | Preparation |  | Included but not measured separately |  | Survey Reference Point
1740 | Cleaning |  | A1.12
1741 | Site Maintenance |  | A1.13
1750 | Disinfection and Testing |  | A1.14
1760 | Warranty Work |  | Included but not measured separately
1770 | Closeout Procedures |  | Included but not measured separately
1780 | Contract Closeout |  | Included but not measured separately
1810 | Equipment Testing and Facility Commissioning |  | A1.15
1810A | Equipment Testing and Facility Commissioning Forms |  | Included but not measured separately
1820 | Demonstration and Training |  | A1.16
1820A | Summary of Training Requirements |  | Included but not measured separately
1820B | Training Schedule |  | Included but not measured separately
1820C | OJT Form |  | Included but not measured separately
1820D | Training Evaluation Form |  | Included but not measured separately
DIV 2 | Site Works
TOC
2230 | Site Preparation for Pipelines, Utilities and Associated Structures |  | A2.01
2232 | Tree Pruning |  | Not Applicable
2240 | Dewatering-General |  | Included but not measured separately
2241 | Provide Water Control Plan Dewatering and Discharge Plan |  | Not Applicable
2242 | Supply Install and Subsequently Remove Dewatering System |  | Not Applicable
2243 | Operate And Maintain Dewatering System |  | Not Applicable
2244 | Retain Specialty Contractor to Monitor Dewatering |  | Not Applicable
2245 | Restoration Works Associated with Dewatering Activities |  | Not Applicable
2246 | Bypass Pumping or Fluming and Unwatering |  | Not Applicable
2260 | Excavation Support Systems |  | A2.02
2261 | Excavation Temporary Support Systems |  | Not Applicable
2300 | Excavating And Backfilling – Structures |  | A2.03
2314 | Tunnelling |  | Not Applicable
2315 | Trenching, Backfilling and Compacting |  | A2.04
2316 | Rock Removal |  | Not Applicable
2317 | Roadway Excavation Embankment and Compaction |  | Not Applicable
2362 | Dust Control |  | A2.05
2389 | Preservation Of Water Courses |  | Not Applicable
2511 | Watermains |  | Not Applicable
2530 | Sewerage |  | A2.06
2531 | Sewage Forcemains |  | Not Applicable
2555 | Cathodic Protection |  | Not Applicable
2631 | Manholes And Catch Basins |  | Not Applicable
2701 | Aggregates – General |  | A2.07
2720 | Untreated Granular Subbase Base Surface and Shoulder |  | A2.08
2725 | Hot Mix Asphalt |  | A2.09
2821 | Chain Link Fences and Gates |  | Not Applicable
2822 | Wire Fences and Gates |  | Not Applicable
2911 | Topsoil And Finish Grading |  | A2.10
2921 | Mechanical Seeding |  | Not Applicable
2922 | Hydraulic Seeding |  | Not Applicable
2933 | Sodding |  | A2.11
2934 | Compost Seeding |  | Not Applicable
2935 | Planting Of Trees, Shrubs and Ground Covers |  | Not Applicable
2936 | Landscape Maintenance |  | Not Applicable
DIV 3 | Concrete
TOC
3100 | Concrete Forms and Accessories |  | Included but not measured separately
3200 | Concrete Reinforcement |  | Included but not measured separately
3300 | Cast in Place Concrete |  | A3.01
3345 | Concrete Curing and Finishing |  | Included but not measured separately
3410 | Plant Precast Structural Concrete |  | Not Applicable
DIV 4 | Masonry
TOC
4051 | Masonry Procedures |  | Not Applicable
4060 | Mortar And Masonry Grout |  | Not Applicable
4080 | Masonry Reinforcement and Connectors |  | Not Applicable
4090 | Masonry Accessories |  | Not Applicable
4211 | Brick Masonry |  | Not Applicable
4220 | Concrete Masonry Units |  | Not Applicable
DIV 5 | Metal
TOC
5050 | Welding |  | Not Applicable
5120 | Structural Steel |  | Not Applicable
5500 | Metal Fabrications – General |  | Included but not measured separately
5501 | Metal Fabrications – Architectural |  | A5.01
5502 | Metal Fabrications – Structural |  | Not Applicable
5503 | Metal Fabrications – Mechanical |  | Not Applicable
5510 | Metal Stairs |  | Included but not measured separately
5512 | Aluminum Handrails |  | A5.02
DIV 6 | Carpentry
TOC
6100 | Rough Carpentry |  | Not Applicable
6200 | Finish Carpentry |  | Not Applicable
DIV 7 | Thermal and Moisture Protection
TOC
7140 | Hot-Applied Rubberized Ashphalt Waterproofing |  | Not Applicable
7160 | Capillary Waterproofing |  | Not Applicable
7200 | Insulation |  | A7.01
7520 | Modified Bituminous Membrane Roofing |  | Not Applicable
7570 | Traffic Topping |  | Not Applicable
7610 | Sheet Metal Roofing |  | Not Applicable
7620 | Sheet Metal Flashing |  | Not Applicable
7700 | Roof Specialties and Accessories |  | Not Applicable
7840 | Firestopping |  | Included but not measured separately
7900 | Joint Sealers |  | Included but not measured separately
DIV 8 | Doors and Windows
TOC
8110 | Steel Doors and Frames |  | Not Applicable
8331 | Overhead Coiling Doors |  | Not Applicable
8410 | Aluminum Doors and Frames |  | Not Applicable
8520 | Windows |  | Not Applicable
8710 | Door Hardware |  | Not Applicable
8800 | Glazing |  | Not Applicable
DIV 9 | Finishes
TOC
9250 | Gypsum Board |  | Not Applicable
9300 | Ceramic Tiling |  | Not Applicable
9510 | Acoustical Ceilings |  | Not Applicable
9522 | Acoustical Treatment (Metal) |  | Not Applicable
9650 | Resilient Tile Flooring |  | Not Applicable
9850 | Chemical Resistant Coatings |  | Not Applicable
9900 | Painting And Protective Coatings |  | A9.01
9960 | Painting Of Steel Tanks and Appurtenances |  | Not Applicable
DIV 10 | Specialties
TOC
10200 | Louvres and Vents |  | Not Applicable
10420 | Fire Extinguishers and Safety Equipment |  | Not Applicable
10800 | Toilet Accessories |  | Not Applicable
10999 | Manufactured Specialties |  | Not Applicable
DIV 11 | Equipment
TOC
11010 | Equipment General Requirements |  | Not Applicable
11240 | Chemical Metering Pumps |  | Not Applicable
11280 | Fabricated Sluice Gates |  | Not Applicable
11282 | Fabricated Slide Gates and Stop Logs |  | Not Applicable
11300 | Submersible Mixers |  | Not Applicable
11374 | Aeration Centrifugal Blowers |  | Not Applicable
11376 | Rotary Positive Displacement Blowers |  | Not Applicable
11377 | Coarse Bubble Air Diffusers |  | Not Applicable
11378 | Fine Bubble Air Diffusers |  | Not Applicable
11410 | Submersible Well Pumps |  | Not Applicable
11421 | Horizontal Split Case Pumps |  | Not Applicable
11422 | Vertical Turbine Pumps |  | Not Applicable
11441 | Submersible Sewage Pumps |  | Not Applicable
11530 | Chemical Storage Tanks |  | Not Applicable
11540 | Liquid Chemical Feed Systems |  | Not Applicable
11580 | Activated Carbon Odour Control Systems |  | Not Applicable
11590 | Automatic Composite Samplers |  | Not Applicable
11601 | Tank Lining Systems |  | Not Applicable
11700 | Elevated Water Storage Tank |  | Not Applicable
11710 | Fibreglass Reinforced Plastic Tanks |  | Not Applicable
11900 | Aboveground Fuel Oil Storage Tanks |  | A11.01
11905 | Fuel Oil System |  | A11.02
DIV 12 | Furnishings
TOC
12345 | Laboratory Casework and Equipment |  | Not Applicable
DIV 13 | SCADA and Instrumentation
TOC
13010 | Process Control General Requirements |  | Included but not measured separately
13050 | Scada Instrumentation and Control Documentation |  | Not Applicable
13105 | General Instrumentation Requirements |  | Included but not measured separately
13110 | Ultrasonic Level Transmitter |  | Not Applicable
13120 | Magnetic Flow Meters |  | Not Applicable
13130 | Float Switch |  | A13.01
13140 | Differential Pressure Transmitter |  | Not Applicable
13150 | Pressure Switch |  | Not Applicable
13160 | Temperature Transmitter |  | Not Applicable
13170 | Sludge Blanket Level |  | Not Applicable
13180 | Turbidity Analyzer |  | Not Applicable
13185 | pH And ORP Analyzer |  | Not Applicable
13190 | Gas Detector |  | Not Applicable
13195 | Chlorine Residual Analyzer |  | Not Applicable
13200 | Gauge Pressure Transmitter |  | Not Applicable
13210 | Fluoride Analyzer |  | Not Applicable
13215 | Chlorine Gas Detectors |  | Not Applicable
13220 | Dissolved Oxygen Analyzer |  | Not Applicable
13230 | Thermal Mass Flow Meters |  | Not Applicable
13240 | Ultrasonic Flow Meter |  | Not Applicable
13250 | Capacitance Level |  | Not Applicable
13251 | Radar Level Transmitter |  | A13.02
13260 | Bubble Level Analyzer |  | Not Applicable
13280 | Weigh Scale |  | Not Applicable
13285 | Depth And Level Pressure Transmitter |  | Not Applicable
13290 | Conductive Level |  | Not Applicable
13295 | Suspended Solids |  | Not Applicable
13305 | Field Wiring |  | A13.03
13310 | Panel Specifications |  | Not Applicable
13311 | Panel – Fat Plan – Template |  | Not Applicable
13390 | Package Control Systems |  | Not Applicable
13400 | Programmable Automation Controllers |  | Not Applicable
13510 | Pcs Scada Local Area Network |  | Not Applicable
13520A | SCADA 900MGZ Wide Area Radio Network |  | Not Applicable
13520B | SCADA 5 8GHZ Wide Area Radio Network |  | Not Applicable
13710 | Security System – Electronic Access Control |  | Not Applicable
13930 | Instrument And Equipment Testing |  | A13.04
DIV 14 | Conveying Systems
TOC
14620 | Hoist, Monorail and Lifting Davit Systems |  | Not Applicable
14620-1 | Hoist/Monorail Data Sheet Hoist, Monorail and Lifting Davit System |  | Not Applicable
14630 | Overhead Traveling Cranes |  | Not Applicable
14630-1 | Crane Data Sheet – Overhead Traveling Cranes |  | Not Applicable
DIV 15 | Mechanical
TOC
15010 | Mechanical General Requirements |  | Included but not measured separately
15075 | Facilities Piping Identification |  | Not Applicable
15080 | Process Piping Insulation |  | Not Applicable
15100 | Plumbing Piping |  | A15.01
15100-01 | Polyvinyl Chloride Drain Waste And Vent |  | A15.02
15100-02 | Cast Iron Soil Pipe (CISP) and Fittings |  | Not Applicable
15100-03 | Acid-Resistant Cast Iron Pipe and Fittings |  | Not Applicable
15100-04 | Acid-Resistant Glass Pipe and Fittings |  | Not Applicable
15100-05 | Acid-Resistant Polypropylene Waste and Vent Pipe and Fittings |  | Not Applicable
15100-06 | Perforated Polyvinyl Chloride (PVC) Pipe and Fittings |  | Not Applicable
15100-07 | High-Density Polyethylene (HDPE) Pipe and Fittings - Gas Service |  | Not Applicable
15100-08 | High Purity Polypropylene (HP-PP) Pipe and Fittings |  | Not Applicable
15100-09 | Carbon Steel Tubing and Fittings |  | Not Applicable
15100-10 | Galvanized Steel Drain and Vent Pipe and Fittings |  | Not Applicable
15200 | Process Piping and Fittings |  | Not Applicable
15200-01 | Cement-Mortar, Glass and Asphaltic-Lined Ductile Iron |  | Not Applicable
15200-02 | Carbon Steel Pipe and Fittings-Special Service |  | Not Applicable
15200-03 | Carbon Steel Pipe and Fittings-General Service |  | Not Applicable
15200-04 | Welded Steel Pipe and Fittings |  | Not Applicable
15200-05 | Glass Rubber, and PP-Lined Pipe, Carbon Steel Pipe And Fittings |  | Not Applicable
15200-06 | PVDF-Lined Steel Pipe and Ductile Iron Fittings |  | Not Applicable
15200-07 | Galvanized Steel Pipe and Malleable Iron Fittings |  | Not Applicable
15200-08 | Stainless Steel Pipe and Fittings-General Service |  | Not Applicable
15200-09 | Stainless Steel Pipe and Fittings-Digester Gas Service |  | Not Applicable
15200-10 | Stainless Steel Pipe and Fittings-Special Service |  | Not Applicable
15200-11 | Polyvinyl Chloride (PVC) Pipe and Fittings |  | Not Applicable
15200-12 | Chlorinated Polyvinyl Chloride (CPVC) Pipe and Fittings |  | Not Applicable
15200-13 | Fiberglass Reinforced Plastic (FRP) Pipe and Fittings |  | Not Applicable
15200-14 | Copper And Copper Alloy Pipe, Tubing, and Fittings |  | A15.03
15200-15 | High Density Polyethylene (HDPE) Pipe and Fittings |  | Not Applicable
15200-16 | Double Wall Containment Piping |  | Not Applicable
15200-17 | PTFE-Lined Steel Pipe And Fittings |  | Not Applicable
15200-18 | Alloy 20 Pipe and Fittings |  | Not Applicable
15200-19 | Polyvinylidene Fluoride (PVDF) Pipe and Fittings |  | Not Applicable
15201 | Piping Support Systems |  | Not Applicable
15204 | Process Piping Specialties |  | Not Applicable
15205 | Process Valves and Operators |  | Not Applicable
15208 | Surge Control Systems (Water) |  | Not Applicable
15410 | Plumbing Fixtures |  | Not Applicable
15440 | Plumbing Equipment |  | A15.04
15500 | Heat Generation |  | Not Applicable
15500-01 | Air Handling Unit |  | Not Applicable
15730 | Unitary Air-Conditioning Equipment |  | Not Applicable
15730-01 | Split System Dx Indoor Units |  | Not Applicable
15730-02 | Ductless Split System Dx Indoor Units |  | Not Applicable
15730-03 | Ductless Split System Dx Outdoor Units |  | Not Applicable
15730-04 | Packaged Indoor Water Source Heat Pump Units |  | Not Applicable
15730-05 | Packaged Roofing Gas Unit Dx Ac Units |  | Not Applicable
15730-06 | Packaged Dx Air Conditioning Units |  | Not Applicable
15730-07 | Room Air Conditioner |  | Not Applicable
15730-08 | Wall Mount Air Conditioner |  | Not Applicable
15730-09 | Packaged Terminal Air Conditioner |  | Not Applicable
15760 | Terminal Heat Transfer Units |  | Not Applicable
15760-01 | Hot Water Unit Heater |  | Not Applicable
15760-02 | Finned Tube Radiators |  | Not Applicable
15760-03 | Cabinet Unit Heater Schedule |  | Not Applicable
15760-04 | Electric Unit Heater |  | Not Applicable
15810 | Metal Ductwork And Accessories |  | Not Applicable
15810-01 | Ductwork Schedule |  | Not Applicable
15810-02 | Sound Attenuator Schedule |  | Not Applicable
15830 | Fans |  | Not Applicable
15830-01 | Fans |  | Not Applicable
15830-02 | Ceiling Fans |  | Not Applicable
15950 | HVAC Systems Testing, Adjusting, and Balancing |  | Not Applicable
15955 | Piping Leakage Testing |  | Not Applicable
DIV 16 | Electrical
TOC
16010 | Electrical General Requirements |  | Included but not measured separately
16015 | Electrical Systems Analysis |  | Not Applicable
16031 | Inspection and Testing |  | Not Applicable
16032 | Motor Control Centre Testing and Commissioning |  | Not Applicable
16050 | Basic Materials & Methods |  | Not Applicable
16051 | Installation Of Cables In Trenches and Ducts |  | A16.01
16120 | Wiring Systems |  | Not Applicable
16122 | Wires and Cables 0-1000V |  | A16.02
16131 | Splitters, Junction, Pull Boxes and Cabinets |  | Not Applicable
16132 | Outlet Boxes, Conduit Boxes and Fittings |  | Not Applicable
16133 | Conduits, Conduit Fastenings and Conduit Fittings |  | A16.03
16141 | Wiring Devices |  | Not Applicable
16145 | Modular Wiring System |  | Not Applicable
16221 | Three Phase Induction Motors |  | Not Applicable
16222 | Motors: 1 To 200 Kw, 575 V |  | Not Applicable
16223 | Motor Starters Up To 600 V |  | Not Applicable
16224 | Variable Frequency Drives To 600 V |  | Not Applicable
16225 | Motor Control Centre |  | Not Applicable
16226 | Reduced Voltage Soft Starters Up To 600V |  | Not Applicable
16231 | Diesel Electric Generating Units (Liquid Cooled) |  | A16.04
16233 | Diesel Electric Generating Units Factory Test Results |  | Not Applicable
16234 | Diesel Electric Generating Units Information Form |  | Not Applicable
16261 | Medium Voltage Reduced Voltage Soft Starters |  | Not Applicable
16262 | Medium Voltage Variable Frequency Drives |  | Not Applicable
16271 | Dry Type Transformers Up To 600 V Primary |  | Not Applicable
16276 | Pad Mounted Distribution Transformers |  | Not Applicable
16289 | Transient Voltage Surge Suppression (TVSS) |  | Not Applicable
16402 | Service Entrance Board |  | Not Applicable
16411 | Air Circuit Breakers |  | Not Applicable
16412 | Molded Case Circuit Breakers |  | Not Applicable
16414 | Disconnect Switches – Fused And Unfused |  | Not Applicable
16441 | Panelboards Breaker Type |  | Not Applicable
16450 | Grounding – Secondary |  | Not Applicable
16480 | Grounding |  | Not Applicable
16496 | Automatic Transfer Switches – Low Voltage |  | Not Applicable
16505 | Lighting Equipment |  | Not Applicable
16670 | Lightning Protection System |  | Not Applicable

## Sheet2
1000 | GENERAL REQUIREMENTS
1010 | SUMMARY OF WORK
1025 | MEASUREMENT AND PAYMENT
1035 | AMENDING AND SUPPLEMENTING CONTRACT DOCUMENTS
1040 | COORDINATION
1060 | REGULATORY REQUIREMENTS
1092 | ABBREVIATIONS
1200 | PROJECT MEETINGS
01200A | PRE-CONSTRUCTION MEETING AGENDA TEMPLATE
1250 | SUBSTITUTIONS
1300 | SUBMITTALS
1310 | CONSTRUCTION SCHEDULES
01310A | FACILITY SCHEDULE TEMPLATE
1351 | HEALTH AND SAFETY
1400 | QUALITY CONTROL
1420 | REFERENCES
1430 | OPERATION AND MAINTENANCE DATA
1450 | AS-BUILT DRAWINGS
01450A | DECLARATION OF COMPLETE AND ACCURATE AS-BUILT DOCUMENTATION
1501 | CONSTRUCTION SEQUENCING
1505 | MOBILIZATION AND DEMOBILIZATION
1520 | FIELD OFFICE
1561 | ENVIRONMENTAL PROTECTION
1600 | MATERIAL AND EQUIPMENT
1740 | CLEANING
1750 | DISINFECTION AND TESTING
1760 | WARRANTY WORK
1770 | CLOSEOUT PROCEDURES
1780 | CONTRACT CLOSEOUT
1810 | EQUIPMENT TESTING AND FACILITY COMMISSIONING | 1
01810A | EQUIPMENT TESTING AND COMMISSIONING FORMS | 1

## Sheet3
16010 | ELECTRICAL GENERAL REQUIREMENTS | Electrical General Requirements | Electrical General Requirements
16015 | ELECTRICAL SYSTEMS ANALYSIS | Electrical Systems Analysis | Electrical Systems Analysis
16031 | INSPECTION AND TESTING | Inspection And Testing | Inspection and Testing
16032 | MOTOR CONTROL CENTRE TESTING AND COMMISSIONING | Motor Control Centre Testing And Commissioning | Motor Control Centre Testing and Commissioning
16050 | BASIC MATERIALS & METHODS | Basic Materials & Methods | Basic Materials & Methods
16051 | INSTALLATION OF CABLES IN TRENCHES AND DUCTS | Installation Of Cables In Trenches And Ducts | Installation Of Cables In Trenches and Ducts
16120 | WIRING SYSTEMS | Wiring Systems | Wiring Systems
16122 | WIRES AND CABLES 0-1000V | Wires And Cables 0-1000V | Wires and Cables 0-1000V
16131 | SPLITTERS, JUNCTION, PULL BOXES AND CABINETS | Splitters, Junction, Pull Boxes And Cabinets | Splitters, Junction, Pull Boxes and Cabinets
16132 | OUTLET BOXES, CONDUIT BOXES AND FITTINGS | Outlet Boxes, Conduit Boxes And Fittings | Outlet Boxes, Conduit Boxes and Fittings
16133 | CONDUITS, CONDUIT FASTENINGS AND CONDUIT FITTINGS | Conduits, Conduit Fastenings And Conduit Fittings | Conduits, Conduit Fastenings and Conduit Fittings
16141 | WIRING DEVICES | Wiring Devices | Wiring Devices
16145 | MODULAR WIRING SYSTEM | Modular Wiring System | Modular Wiring System
16221 | THREE PHASE INDUCTION MOTORS | Three Phase Induction Motors | Three Phase Induction Motors
16222 | MOTORS: 1 TO 200 KW, 575 V | Motors: 1 To 200 Kw, 575 V | Motors: 1 To 200 Kw, 575 V
16223 | MOTOR STARTERS UP TO 600 V | Motor Starters Up To 600 V | Motor Starters Up To 600 V
16224 | VARIABLE FREQUENCY DRIVES TO 600 V | Variable Frequency Drives To 600 V | Variable Frequency Drives To 600 V
16225 | MOTOR CONTROL CENTRE | Motor Control Centre | Motor Control Centre
16226 | REDUCED VOLTAGE SOFT STARTERS UP TO 600V | Reduced Voltage Soft Starters Up To 600V | Reduced Voltage Soft Starters Up To 600V
16231 | DIESEL ELECTRIC GENERATING UNITS (LIQUID COOLED) | Diesel Electric Generating Units (Liquid Cooled) | Diesel Electric Generating Units (Liquid Cooled)
16233 | DIESEL ELECTRIC GENERATING UNITS FACTORY TEST RESULTS | Diesel Electric Generating Units Factory Test Results | Diesel Electric Generating Units Factory Test Results
16234 | DIESEL ELECTRIC GENERATING UNITS INFORMATION FORM | Diesel Electric Generating Units Information Form | Diesel Electric Generating Units Information Form
16261 | MEDIUM VOLTAGE REDUCED VOLTAGE SOFT STARTERS | Medium Voltage Reduced Voltage Soft Starters | Medium Voltage Reduced Voltage Soft Starters
16262 | MEDIUM VOLTAGE VARIABLE FREQUENCY DRIVES | Medium Voltage Variable Frequency Drives | Medium Voltage Variable Frequency Drives
16271 | DRY TYPE TRANSFORMERS UP TO 600 V PRIMARY | Dry Type Transformers Up To 600 V Primary | Dry Type Transformers Up To 600 V Primary
16276 | PAD MOUNTED DISTRIBUTION TRANSFORMERS | Pad Mounted Distribution Transformers | Pad Mounted Distribution Transformers
16289 | TRANSIENT VOLTAGE SURGE SUPPRESSION (TVSS) | Transient Voltage Surge Suppression (Tvss) | Transient Voltage Surge Suppression (TVSS)
16402 | SERVICE ENTRANCE BOARD | Service Entrance Board | Service Entrance Board
16411 | AIR CIRCUIT BREAKERS | Air Circuit Breakers | Air Circuit Breakers
16412 | MOLDED CASE CIRCUIT BREAKERS | Molded Case Circuit Breakers | Molded Case Circuit Breakers
16414 | DISCONNECT SWITCHES – FUSED AND UNFUSED | Disconnect Switches – Fused And Unfused | Disconnect Switches – Fused And Unfused
16441 | PANELBOARDS BREAKER TYPE | Panelboards Breaker Type | Panelboards Breaker Type
16450 | GROUNDING – SECONDARY | Grounding – Secondary | Grounding – Secondary
16480 | GROUNDING | Grounding | Grounding
16496 | AUTOMATIC TRANSFER SWITCHES – LOW VOLTAGE | Automatic Transfer Switches – Low Voltage | Automatic Transfer Switches – Low Voltage
16505 | LIGHTING EQUIPMENT | Lighting Equipment | Lighting Equipment
16670 | LIGHTNING PROTECTION SYSTEM | Lightning Protection System | Lightning Protection System